Senior Project Status Update 5/23/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | In Progress | 4/16/11 |  | 5/16/11 | 5/30/11 |  |  | 30 |  | 5:10 |
| Requirements Specification | Not Yet Started | 5/31/11 |  |  | 6/2/11 |  |  | 5 |  | 0 |
| Design | Not Yet Started | 6/3/11 |  |  | 6/17/11 |  |  | 25 |  | 0 |
| Coding | Not Yet Started | 6/18/11 |  |  | 7/9/11 |  |  | 35 |  | 0 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 204:15 |
| **Accomplishments** I have been researching about how to create a service that will run in the background. I have also found out how to change the volume of the ringer. | | | | | | | | | | |
| **Problems** I’m having problems finding time to work on my project. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** No changes to scope, schedule or cost. | | | | | | | | | | |
| **Confessional** Increase in hours 5:01. Total planned hours 314. I am currently a bit behind schedule.  As mentioned previously I’m having difficulties finding time to work on my project. I plan to remedy this by getting up earlier and working on my project in the mornings before I start work. | | | | | | | | | | |
| **Scripture** Proverbs 22:13 The slothful man saith, There is a lion without, I shall be slain in the streets.  *My senior project is a bit like a lion. I need to overcome my slothful nature to avoid being slain.* | | | | | | | | | | |