Senior Project Status Update 5/30/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | In Progress | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 |  | 30 |  | 22:52 |
| Requirements Specification | Not Yet Started | 5/31/11 |  |  | 6/2/11 |  |  | 5 |  | 0 |
| Design | Not Yet Started | 6/3/11 |  |  | 6/17/11 |  |  | 25 |  | 0 |
| Coding | Not Yet Started | 6/18/11 |  |  | 7/9/11 |  |  | 35 |  | 0 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 221:57 |
| **Accomplishments** I am fairly certain that I know now how I will schedule the ringtone to change. I have been working on prototypes to schedule the ringtone and I am able to successfully change the ringtone and in another prototype schedule an event to happen. | | | | | | | | | | |
| **Problems** I have no problems I am working with at this time. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I am pushing back my research a day. I have just a little bit more that I would like to research. I still plan to start the requirements specification at the planned time. | | | | | | | | | | |
| **Confessional** Increase in hours 17:42. Total planned hours 314. I am currently a bit behind schedule.  I have been working on prototypes this week and trying to figure out the best way to schedule events to happen. I have also figured out how to change the ringtone and enable the vibrator for the different types of rings. | | | | | | | | | | |
| **Scripture** Doctrine & Covenants 38:30 I tell you these things because of your prayers; wherefore, treasure up wisdom in your bosoms… …if ye are prepared ye shall not fear. | | | | | | | | | | |