Senior Project Status Update 6/13/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | Complete | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 | 5/31/11 | 30 |  | 26:14 |
| Requirements Specification | Complete | 5/31/11 | 6/1/11 | 6/1/11 | 6/2/11 |  | 6/2/11 | 5 |  | 4:36 |
| Design | In Progress | 6/3/11 |  | 6/3/11 | 6/17/11 |  |  | 25 |  | 14:54 |
| Coding | Not Yet Started | 6/18/11 |  |  | 7/9/11 |  |  | 35 |  | 0 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 244:49 |
| **Accomplishments** I have created a design that will satisfy all my requirements. I have also designed how the UI will look. | | | | | | | | | | |
| **Problems** I have no problems I am working with at this time. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I have no changes to scope, schedule or cost this week. | | | | | | | | | | |
| **Confessional** Increase in hours 11:50. Total planned hours 314. I am on schedule.  Designing is going a lot quicker that I thought. I believe this is because of my previously attempted senior project. I believe that later this week I may switch over to coding for a time and at least get some stub code created. I hope that this will help to solidify my design and raise awareness of issues that my current design may have. I plan that on encountering some issues that may need more design or even research. When those issues arise I will complete a mini cycle and go through the research and design or just design phase again. I believe that having these mini iterations may help me to achieve my goal quicker. | | | | | | | | | | |
| **Scripture** Doctrine and Covenants 88:124 Cease to be idle; cease to be unclean; cease to find fault one with another; cease to sleep longer than is needful; retire to thy bed early, that ye may not be weary; arise early that your bodies and your minds may be invigorated.  *I have been getting up early these last few weeks so that I can get some work done while everyone else is sleeping.* | | | | | | | | | | |