Senior Project Status Update 6/27/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | Complete | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 | 5/31/11 | 30 |  | 26:14 |
| Requirements Specification | Complete | 5/31/11 | 6/1/11 | 6/1/11 | 6/2/11 |  | 6/2/11 | 5 |  | 4:36 |
| Design | Complete | 6/3/11 |  | 6/3/11 | 6/17/11 |  | 6/17/11 | 25 |  | 22:19 |
| Coding | In Progress | 6/18/11 |  | 6/18/11 | 7/9/11 |  |  | 35 |  | 13:12 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 263:56 |
| **Accomplishments** I am working on getting the UI setup so that I can add edit and delete events. I currently have half the UI to edit/add events I now need to be able to delete events which shouldn’t be much more work. | | | | | | | | | | |
| **Problems** I have no problems I am working with at this time. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I have no changes to scope, schedule or cost this week. | | | | | | | | | | |
| **Confessional** Increase in hours 9:24. Total planned hours 314. I am behind schedule.  I have been able to create my database and I have the UI created to add edit and delete events. I am working on wiring the UI so that when I save the changes for an event they are saved to the database. Once I’m done with that part I’m planning on writing the service that will run and reschedule the events. Although I don’t feel there is too much more to do I’m a bit concerned that I am running out of time and I’m not as far along as I would like. | | | | | | | | | | |
| **Scripture** Matthew 25:1-2 1. Then shall the kingdom of heaven be likened unto ten virgins which took their lamps and went forth to meet the bridegroom 2. And five of them were wise, and five were foolish. *I’m working hard to be one of the “wise virgins” who are ready.* | | | | | | | | | | |