Senior Project Status Update 7/4/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | Complete | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 | 5/31/11 | 30 |  | 26:14 |
| Requirements Specification | Complete | 5/31/11 | 6/1/11 | 6/1/11 | 6/2/11 |  | 6/2/11 | 5 |  | 4:36 |
| Design | Complete | 6/3/11 |  | 6/3/11 | 6/17/11 |  | 6/17/11 | 25 |  | 22:19 |
| Coding | In Progress | 6/18/11 |  | 6/18/11 | 7/9/11 |  |  | 35 |  | 22:04 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 274:18 |
| **Accomplishments** I have rewritten all the lost code but not much more. | | | | | | | | | | |
| **Problems** Earlier this week I deleted a considerable amount of code. I had thought that I had it backed up in SVN but it wasn’t. I have spent half the week recovering the code. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I have no changes to scope, schedule or cost this week. | | | | | | | | | | |
| **Confessional** Increase in hours 10:22. Total planned hours 314. I am behind schedule.  I have been able to rewrite all the code that I deleted. I have also learned a lot about subversion. Unfortunately I am not as far along as I would have liked to be so I plan to put a few extra hours in this week to get caught up. | | | | | | | | | | |
| **Scripture** Mosiah 22:16 And after [I] had pursued [it] two days, [I] could no longer follow [its] tracks; therefore [it was] lost in the wilderness. | | | | | | | | | | |