Senior Project Status Update 6/20/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | Complete | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 | 5/31/11 | 30 |  | 26:14 |
| Requirements Specification | Complete | 5/31/11 | 6/1/11 | 6/1/11 | 6/2/11 |  | 6/2/11 | 5 |  | 4:36 |
| Design | Complete | 6/3/11 |  | 6/3/11 | 6/17/11 |  | 6/17/11 | 25 |  | 22:19 |
| Coding | In Progress | 6/18/11 |  | 6/18/11 | 7/9/11 |  |  | 35 |  | 2:18 |
| Testing | Not Yet Started | 7/10/11 |  |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 254:32 |
| **Accomplishments** I have “finished” the design. I have started the coding task. I have also just about gotten my Database all setup. | | | | | | | | | | |
| **Problems** I have no problems I am working with at this time. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I have no changes to scope, schedule or cost this week. | | | | | | | | | | |
| **Confessional** Increase in hours 9:43. Total planned hours 314. I am on schedule.  I didn’t realize when I had written my last status update how quickly I had planned on starting the coding task. I believe that I have finished my design but it feels like there is something still missing. I hope to find that quickly so it doesn’t too large of an impact on what I am coding. This last week I had gotten a few less hours than I had planned. I had gotten sick one day last week but luckily it was only one day and I was feeling good enough to continue on the next day. This last week I had figured out how to get the Database all setup. | | | | | | | | | | |
| **Scripture** Moroni 6:4 And after they had been received unto baptism, and were wrought upon and [cleansed](http://lds.org/scriptures/bofm/moro/6?lang=eng) by the power of the Holy Ghost, they were numbered among the people of the [church](http://lds.org/scriptures/bofm/moro/6?lang=eng) of Christ; and their [names](http://lds.org/scriptures/bofm/moro/6?lang=eng) were taken, that they might be remembered and nourished by the good word of God… *Through my research phase I kept good notes to hopefully help me remember.* | | | | | | | | | | |