Senior Project Status Update 7/11/11

Kevin Cherrington

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current Status | Start Date | | | Stop Date | | | Number of Hours | | |
| Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual |
| Previous Sr. Project Attempt | Complete |  |  |  |  |  |  |  |  | 192:21 |
| Preliminary Research and Proposal Preparation | Complete | 4/15/11 |  | 4/15/11 | 5/15/11 |  | 5/14/11 | 10 |  | 6:44 |
| Research | Complete | 4/16/11 |  | 5/16/11 | 5/30/11 | 5/31/11 | 5/31/11 | 30 |  | 26:14 |
| Requirements Specification | Complete | 5/31/11 | 6/1/11 | 6/1/11 | 6/2/11 |  | 6/2/11 | 5 |  | 4:36 |
| Design | Complete | 6/3/11 |  | 6/3/11 | 6/17/11 |  | 6/17/11 | 25 |  | 22:19 |
| Coding | In Progress | 6/18/11 |  | 6/18/11 | 7/9/11 | 7/12/11 |  | 35 |  | 34:26 |
| Testing | Not Yet Started | 7/10/11 | 7/13/11 |  | 7/20/11 |  |  | 17 |  | 0 |
| **Total Hours** |  |  |  |  |  |  |  | 314 |  | 286:24 |
| **Accomplishments** I have been integrating a lot of testing into my coding so I don’t have much to test in terms of the GUI and the database. I am very close to being done coding. | | | | | | | | | | |
| **Problems** I went on vacation last week and I tried really hard to stay caught up and catch up on past work that I had missed but I still need to push back the testing deadline. | | | | | | | | | | |
| **Changes in Scope, Schedule, and Cost** I am moving testing to start on Wednesday. | | | | | | | | | | |
| **Confessional** Increase in hours 12:06. Total planned hours 314. I am behind schedule.  As I mentioned I was vacationing last week and I didn’t get as much done as I would have hoped. Because of that I am still in the coding phase I need another day to finish coding and then I will start the testing/debugging phase on Wednesday. Also as mentioned I have been doing some testing along the way so hopefully it won’t need quite as much. | | | | | | | | | | |
| **Scripture** Daniel 1:12 Prove thy [code], I beseech thee, ten days; and let them give us pulse to eat, and water to drink. | | | | | | | | | | |